## Sheet1
Partner | Point Type | State | LGA | Ward (GRID3) | Ward (OCHA/COD) | Cluster ID | Survey ID | Status | Sequence | Latitude | Longitude | Building ID | Building Confidence | IDP Category | IOM Site Name | IOM Site Type | Site Radius (m) | Target HHs (primary) | Reserve HHs | Notes | Achieved | Date Collected | Collection Status | Comment
NRC | Non-IDP household (primary) | Borno | Jere | Dala | Dala | non_idp_NG008013_2 | non_idp_NG008013_2_HH01 | Primary | 1 | 11.729168381569822 | 13.084322500763554 | nga_buildings_part3_0000261244 | 0.8272 | [7 empty] | No |  | Not started | Military Base
NRC | Non-IDP household (primary) | Borno | Jere | Dala | Dala | non_idp_NG008013_2 | non_idp_NG008013_2_HH02 | Primary | 2 | 11.727806747867016 | 13.0840556840567 | nga_buildings_part3_0000261240 | 0.9211 | [7 empty] | No |  | Not started | Military Base
NRC | Non-IDP household (primary) | Borno | Jere | Ajiri | Galtimari | non_idp_NG008013_2 | non_idp_NG008013_2_HH03 | Primary | 3 | 11.727303284527808 | 13.085196477657348 | nga_buildings_part3_0000261274 | 0.8351 | [7 empty] | No |  | Not started | Military Base
NRC | Non-IDP household (primary) | Borno | Jere | Dala | Dala | non_idp_NG008013_2 | non_idp_NG008013_2_HH04 | Primary | 4 | 11.72659580107713 | 13.083042517625826 | nga_buildings_part3_0000261290 | 0.8595 | [7 empty] | No |  | Not started | Military Base
NRC | Non-IDP household (primary) | Borno | Jere | Ajiri | Galtimari | non_idp_NG008013_2 | non_idp_NG008013_2_HH05 | Primary | 5 | 11.724381864256 | 13.085726741296908 | nga_buildings_part3_0000261213 | 0.9201 | [7 empty] | No |  | Not started | Military Base
NRC | Non-IDP household (primary) | Borno | Jere | Dala | Dala | non_idp_NG008013_2 | non_idp_NG008013_2_HH06 | Primary | 6 | 11.725415767703684 | 13.08241746910032 | nga_buildings_part3_0000261263 | 0.9423 | [7 empty] | No |  | Not started | Military Base
NRC | IDP cluster (Tier 1 primary) | Borno | Konduga | Dalori | Dalori | idp_NG008016_7 |  | Primary |  | 11.754859010155991 | 13.262015964150416 |  |  | In-host | Dalori Village | Host Community | NA | 6 | 6 |  | 4 of 6 | 2026-09-02 | Partial | To be done today
NRC | IDP cluster (Tier 1 primary) | Borno | Konduga | Dalori | Dalori | idp_NG008016_8 |  | Primary |  | 11.734580010121585 | 13.283329964129408 |  |  | In-camp | Kalari Abule | Collective Settlement/Centre | NA | 6 | 6 |  | 4 of 6 | 2026-09-02 | Partial | To be done today
NRC | IDP cluster (Tier 1 primary) | Borno | Konduga | Auno | Yajiwa | idp_NG008016_supp5 |  | Primary |  | 11.849660010261674 | 13.022899964368852 |  |  | In-host | Jimtilo | Host Community | 150 | 6 | 6 |  | 5 of 6 | 2026-09-15 | Partial | Done
NRC | IDP cluster (Tier 1 primary) | Borno | Konduga | Auno | Yajiwa | idp_NG008016_supp6 |  | Primary |  | 11.998453010543706 | 12.957878964446143 |  |  | In-host | Subdo Buraye | Integrated Sites | 150 | 6 | 6 |  | 3 of 6 | 2026-09-16 | Partial | Done
NRC | IDP cluster (Tier 1 primary) | Borno | Konduga | Auno | Yajiwa | idp_NG008016_supp7 |  | Primary |  | 12.03690001066739 | 13.069649964355603 |  |  | In-host | Tungushe Gana A | Host Community | 150 | 6 | 6 |  | 4 of 6 | 2026-09-16 | Partial | Done
NRC | IDP cluster (Tier 1 primary) | Borno | Konduga | Yale | Konduga | idp_NG008016_supp8 |  | Primary |  | 11.664530010016852 | 13.396049964023616 |  |  | In-camp | Boarding School | Collective Settlement/Centre | 150 | 6 | 6 |  | 0 of 6 |  | Not started | Done
NRC | Non-IDP household (primary) | Borno | Konduga | Dalori | Dalori | non_idp_NG008016_11 | non_idp_NG008016_11_HH01 | Primary | 1 | 11.76190697219078 | 13.303396387121811 | nga_buildings_part3_0000291186 | 0.8615 | [7 empty] | No |  | Not started | Not Accessible
NRC | Non-IDP household (primary) | Borno | Konduga | Dalori | Dalori | non_idp_NG008016_11 | non_idp_NG008016_11_HH06 | Primary | 6 | 11.745058481878386 | 13.3022709765465 | nga_buildings_part3_0000290531 | 0.8739 | [7 empty] | No |  | Not started | Not Accessible
NRC | Non-IDP household (primary) | Borno | Konduga | Jakana | Jakana | non_idp_NG008016_16 | non_idp_NG008016_16_HH01 | Primary | 1 | 11.842847744627573 | 12.70977938514014 | nga_buildings_part2_0001110745 | 0.7676 | [7 empty] | No |  | Not started | Not Accessible
NRC | Non-IDP household (primary) | Borno | Konduga | Jakana | Jakana | non_idp_NG008016_16 | non_idp_NG008016_16_HH02 | Primary | 2 | 11.842426801036956 | 12.688568053459834 | nga_buildings_part2_0001110785 | 0.793 | [7 empty] | No |  | Not started | Not Accessible
NRC | Non-IDP household (primary) | Borno | Konduga | Jakana | Jakana | non_idp_NG008016_16 | non_idp_NG008016_16_HH03 | Primary | 3 | 11.842261216851822 | 12.688358351479875 | nga_buildings_part2_0001110805 | 0.7833 | [7 empty] | No |  | Not started | Not Accessible
NRC | Non-IDP household (primary) | Borno | Konduga | Jakana | Jakana | non_idp_NG008016_16 | non_idp_NG008016_16_HH04 | Primary | 4 | 11.842575448242352 | 12.71017488932446 | nga_buildings_part2_0001110743 | 0.7647 | [7 empty] | No |  | Not started | Not Accessible
NRC | Non-IDP household (primary) | Borno | Konduga | Jakana | Jakana | non_idp_NG008016_16 | non_idp_NG008016_16_HH05 | Primary | 5 | 11.8387027036192 | 12.711180391138305 | nga_buildings_part2_0001110763 | 0.796 | [7 empty] | No |  | Not started | Not Accessible
NRC | Non-IDP household (primary) | Borno | Konduga | Jakana | Jakana | non_idp_NG008016_16 | non_idp_NG008016_16_HH06 | Primary | 6 | 11.842937057126797 | 12.709903180138795 | nga_buildings_part2_0001110746 | 0.7643 | [7 empty] | No |  | Not started | Not Accessible
NRC | Non-IDP household (primary) | Borno | Konduga | Auno | Auno | non_idp_NG008016_9 | non_idp_NG008016_9_HH05 | Primary | 5 | 11.829380021155702 | 13.066915549105495 | nga_buildings_part2_0000967421 | 0.7502 | [7 empty] | No |  | Not started | Done
NRC | Non-IDP household (primary) | Borno | Konduga | Auno | Jakana | non_idp_NG008016_supp2 | non_idp_NG008016_supp2_HH01 | Primary | 1 | 11.845324026718988 | 12.936369102940215 | nga_buildings_part2_0000022992 | 0.7831 | [7 empty] | No |  | Not started | Done
NRC | Non-IDP household (primary) | Borno | Konduga | Auno | Jakana | non_idp_NG008016_supp2 | non_idp_NG008016_supp2_HH02 | Primary | 2 | 11.848608704918632 | 12.919029900601403 | nga_buildings_part2_0000022575 | 0.9184 | [7 empty] | No |  | Not started | Done
NRC | Non-IDP household (primary) | Borno | Konduga | Auno | Jakana | non_idp_NG008016_supp2 | non_idp_NG008016_supp2_HH03 | Primary | 3 | 11.847608693781549 | 12.942900590152805 | nga_buildings_part2_0000022953 | 0.7977 | [7 empty] | No |  | Not started | Done
NRC | Non-IDP household (primary) | Borno | Konduga | Auno | Jakana | non_idp_NG008016_supp2 | non_idp_NG008016_supp2_HH04 | Primary | 4 | 11.84474954821741 | 12.937430960942626 | nga_buildings_part2_0000022994 | 0.8347 | [7 empty] | No |  | Not started | Done
NRC | Non-IDP household (primary) | Borno | Konduga | Auno | Jakana | non_idp_NG008016_supp2 | non_idp_NG008016_supp2_HH05 | Primary | 5 | 11.845330009905611 | 12.926841603338488 | nga_buildings_part2_0000022533 | 0.7527 | [7 empty] | No |  | Not started | Done
NRC | Non-IDP household (primary) | Borno | Konduga | Auno | Jakana | non_idp_NG008016_supp2 | non_idp_NG008016_supp2_HH06 | Primary | 6 | 11.847330260726787 | 12.94398414343797 | nga_buildings_part2_0000022942 | 0.8105 | [7 empty] | No |  | Not started | Done
NRC | Non-IDP household (primary) | Borno | Konduga | Abbaram | Kawuri | non_idp_NG008016_supp3 | non_idp_NG008016_supp3_HH01 | Primary | 1 | 11.725754263494558 | 13.721115470112816 | nga_buildings_part3_0000012790 | 0.8477 | [7 empty] | No |  | Not started | Accessible but No Residence in the area to conduct the assessment for
NRC | Non-IDP household (primary) | Borno | Konduga | Abbaram | Kawuri | non_idp_NG008016_supp3 | non_idp_NG008016_supp3_HH02 | Primary | 2 | 11.73963535811398 | 13.730867165387345 | nga_buildings_part3_0000012787 | 0.7569 | [7 empty] | No |  | Not started | Accessible but No Residence in the area to conduct the assessment for
NRC | Non-IDP household (primary) | Borno | Konduga | Abbaram | Kawuri | non_idp_NG008016_supp3 | non_idp_NG008016_supp3_HH03 | Primary | 3 | 11.724394568829918 | 13.726573301965004 | nga_buildings_part3_0000012788 | 0.8076 | [7 empty] | No |  | Not started | Accessible but No Residence in the area to conduct the assessment for
NRC | Non-IDP household (primary) | Borno | Konduga | Abbaram | Kawuri | non_idp_NG008016_supp3 | non_idp_NG008016_supp3_HH04 | Primary | 4 | 11.724669403933266 | 13.725863348767776 | nga_buildings_part3_0000012789 | 0.8375 | [7 empty] | No |  | Not started | Accessible but No Residence in the area to conduct the assessment for
NRC | Non-IDP household (primary) | Borno | Konduga | Abbaram | Kawuri | non_idp_NG008016_supp4 | non_idp_NG008016_supp4_HH01 | Primary | 1 | 11.64235899586301 | 13.613448675904332 | nga_buildings_part3_0000012802 | 0.81 | [7 empty] | No |  | Not started | Accessible but No Residence in the area to conduct the assessment for
NRC | Non-IDP household (primary) | Borno | Konduga | Abbaram | Kawuri | non_idp_NG008016_supp4 | non_idp_NG008016_supp4_HH02 | Primary | 2 | 11.641958168597451 | 13.613958343035016 | nga_buildings_part3_0000012804 | 0.7903 | [7 empty] | No |  | Not started | Accessible but No Residence in the area to conduct the assessment for
NRC | Non-IDP household (primary) | Borno | Konduga | Abbaram | Kawuri | non_idp_NG008016_supp4 | non_idp_NG008016_supp4_HH03 | Primary | 3 | 11.646215284005889 | 13.612508379105892 | nga_buildings_part3_0000012805 | 0.8114 | [7 empty] | No |  | Not started | Accessible but No Residence in the area to conduct the assessment for
NRC | Non-IDP household (primary) | Borno | Konduga | Abbaram | Kawuri | non_idp_NG008016_supp4 | non_idp_NG008016_supp4_HH04 | Primary | 4 | 11.6421350713529 | 13.613296831368382 | nga_buildings_part3_0000012801 | 0.7633 | [7 empty] | No |  | Not started | Accessible but No Residence in the area to conduct the assessment for
NRC | Non-IDP household (primary) | Borno | Konduga | Abbaram | Kawuri | non_idp_NG008016_supp4 | non_idp_NG008016_supp4_HH05 | Primary | 5 | 11.645684886289224 | 13.612037471250757 | nga_buildings_part3_0000012806 | 0.777 | [7 empty] | No |  | Not started | Accessible but No Residence in the area to conduct the assessment for
NRC | Non-IDP household (primary) | Borno | Konduga | Abbaram | Kawuri | non_idp_NG008016_supp4 | non_idp_NG008016_supp4_HH06 | Primary | 6 | 11.645356856557823 | 13.612784714338243 | nga_buildings_part3_0000012803 | 0.8116 | [7 empty] | No |  | Not started | Accessible but No Residence in the area to conduct the assessment for
NRC | Non-IDP household (primary) | Borno | Konduga | Ajiri | Ajiri | non_idp_NG008016_supp5 | non_idp_NG008016_supp5_HH01 | Primary | 1 | 11.657743384341822 | 13.250238481959896 | nga_buildings_part3_0000012811 | 0.8216 | [7 empty] | No |  | Not started | Accessible but No Residence in the area to conduct the assessment for
NRC | Non-IDP household (primary) | Borno | Konduga | Ajiri | Ajiri | non_idp_NG008016_supp5 | non_idp_NG008016_supp5_HH02 | Primary | 2 | 11.65651927193964 | 13.2469538071505 | nga_buildings_part3_0000012809 | 0.7673 | [7 empty] | No |  | Not started | Accessible but No Residence in the area to conduct the assessment for
NRC | Non-IDP household (primary) | Borno | Konduga | Ajiri | Ajiri | non_idp_NG008016_supp5 | non_idp_NG008016_supp5_HH03 | Primary | 3 | 11.65358605293897 | 13.251145249647204 | nga_buildings_part3_0000012813 | 0.7598 | [7 empty] | No |  | Not started | Accessible but No Residence in the area to conduct the assessment for
NRC | Non-IDP household (primary) | Borno | Konduga | Ajiri | Ajiri | non_idp_NG008016_supp5 | non_idp_NG008016_supp5_HH04 | Primary | 4 | 11.653626532119826 | 13.251053823122843 | nga_buildings_part3_0000012812 | 0.7615 | [7 empty] | No |  | Not started | Accessible but No Residence in the area to conduct the assessment for
NRC | Non-IDP household (primary) | Borno | Konduga | Ajiri | Ajiri | non_idp_NG008016_supp5 | non_idp_NG008016_supp5_HH05 | Primary | 5 | 11.65360394594284 | 13.25091895214711 | nga_buildings_part3_0000012816 | 0.8029 | [7 empty] | No |  | Not started | Accessible but No Residence in the area to conduct the assessment for
NRC | Non-IDP household (primary) | Borno | Konduga | Ajiri | Ajiri | non_idp_NG008016_supp5 | non_idp_NG008016_supp5_HH06 | Primary | 6 | 11.655915907054403 | 13.247892771881858 | nga_buildings_part3_0000012808 | 0.833 | [7 empty] | No |  | Not started | Accessible but No Residence in the area to conduct the assessment for
NRC | Non-IDP household (primary) | Borno | Konduga | Dalori | Dalori | non_idp_NG008016_supp6 | non_idp_NG008016_supp6_HH01 | Primary | 1 | 11.763019950671485 | 13.265410296649986 | nga_buildings_part3_0000013318 | 0.7786 | [7 empty] | No |  | Not started | Not on Kobocollect
NRC | Non-IDP household (primary) | Borno | Konduga | Dalori | Dalori | non_idp_NG008016_supp6 | non_idp_NG008016_supp6_HH02 | Primary | 2 | 11.755583126723112 | 13.261128311785097 | nga_buildings_part3_0000013907 | 0.7574 | [7 empty] | No |  | Not started | Not on Kobocollect
NRC | Non-IDP household (primary) | Borno | Konduga | Dalori | Dalori | non_idp_NG008016_supp6 | non_idp_NG008016_supp6_HH03 | Primary | 3 | 11.761212507697175 | 13.267659351335334 | nga_buildings_part3_0000013169 | 0.754 | [7 empty] | No |  | Not started | Not on Kobocollect
NRC | Non-IDP household (primary) | Borno | Konduga | Dalori | Dalori | non_idp_NG008016_supp6 | non_idp_NG008016_supp6_HH04 | Primary | 4 | 11.75745542168497 | 13.264876618334355 | nga_buildings_part3_0000013348 | 0.7695 | [7 empty] | No |  | Not started | Not on Kobocollect
NRC | Non-IDP household (primary) | Borno | Konduga | Dalori | Dalori | non_idp_NG008016_supp6 | non_idp_NG008016_supp6_HH05 | Primary | 5 | 11.756991346966675 | 13.26508358824587 | nga_buildings_part3_0000013349 | 0.7854 | [7 empty] | No |  | Not started | Not on Kobocollect
NRC | Non-IDP household (primary) | Borno | Konduga | Dalori | Dalori | non_idp_NG008016_supp6 | non_idp_NG008016_supp6_HH06 | Primary | 6 | 11.757368802163754 | 13.265552393150797 | nga_buildings_part3_0000013328 | 0.7842 | [7 empty] | No |  | Not started | Not on Kobocollect